## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 68
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Austin - Add Trail and Finishing Touches to Fireball | 16 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 2; Days (Points Completed) 4: 2; Days (Points Completed) 5: 1; Days (Points Completed) 6: 1; Days (Points Completed) 7: 2; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 4; Days (Points Completed) 11: 2 | 2 | 87.5%
Cleaning Existing Modes & Dungeon Level Creation | 20 | Days (Points Completed) 1: 5; Days (Points Completed) 2: 4; Days (Points Completed) 3: 3; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 9; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0; Days (Points Completed) 11: 0 | -1 | 105%
In game pop-up UI (prototype)(Joseph) | 20 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 2; Days (Points Completed) 10: 4; Days (Points Completed) 11: 6 | 8 | 60%
Main Menu (Full functionality) | 12 | [20 empty] | 12 | 0%
Feature 5 | [21 empty] | 0
Feature 6 | [21 empty] | 0
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 68 | 63 | 59 | 54 | 52 | 51 | 41 | 39 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21 | 69.12%
Ideal Trend | 68 | 64.6 | 61.2 | 57.8 | 54.4 | 51 | 47.6 | 44.2 | 40.8 | 37.4 | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 1.3323e-14
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days