## Current Iteration
|  | Iteration Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 143
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Invisibility and Fireball Power Up | 22 | [20 empty] | 22 | 0%
Animations | 15 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 2; Days (Points Completed) 3: 4; Days (Points Completed) 4: 3; Days (Points Completed) 5: 4.5; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0 | 1.5 | 90%
Dungeon Level Design | 80 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 13; Days (Points Completed) 7: 6; Days (Points Completed) 8: 3; Days (Points Completed) 9: 4.5; Days (Points Completed) 10: 5 | 48.5 | 39.38%
Main Menu | 12 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 2; Days (Points Completed) 8: 1; Days (Points Completed) 9: 2; Days (Points Completed) 10: 3 | 0 | 100%
Gameplay UI | 14 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 2; Days (Points Completed) 8: 1; Days (Points Completed) 9: 2; Days (Points Completed) 10: 3 | 2 | 85.71%
Feature 6 | [21 empty] | 0
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 143 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 74 | 48.25%
Ideal Trend | 143 | 128.7 | 114.4 | 100.1 | 85.8 | 71.5 | 57.2 | 42.9 | 28.6 | 14.3 | 3.5527e-15 | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days