## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 88
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Austin - Add Trail and Finishing Touches to Fireball | 16 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 2; Days (Points Completed) 4: 2; Days (Points Completed) 5: 1; Days (Points Completed) 6: 1; Days (Points Completed) 7: 2; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 4; Days (Points Completed) 11: 2 | 2 | 87.5%
Cleaning Existing Modes & Dungeon Level Creation | 40 | [20 empty] | 40 | 0%
In game pop-up UI (prototype) | 20 | [20 empty] | 20 | 0%
Main Menu (Full functionality) | 12 | [20 empty] | 12 | 0%
Feature 5 | [21 empty] | 0
Feature 6 | [21 empty] | 0
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 88 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 74 | 15.91%
Ideal Trend | 88 | 83.6 | 79.2 | 74.8 | 70.4 | 66 | 61.6 | 57.2 | 52.8 | 48.4 | 44 | 39.6 | 35.2 | 30.8 | 26.4 | 22 | 17.6 | 13.2 | 8.8 | 4.4 | -1.4211e-14
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days