## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 110
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Main Menu Prototype - Jerry Nelson & Braydon Roberts | 24 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | -1 | 3 | [6 empty] | 0 | 100%
Dungeon Level Concept - Joseph Earl | 70 | Days (Points Completed) 1: 13 | 57 | 18.57%
Game Mode Organization and Polishing - Austin | 16 | [20 empty] | 16 | 0%
Feature 4 | [21 empty] | 0
Feature 5 | [21 empty] | 0
Feature 6 | [21 empty] | 0
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 110 | 97 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 73 | 33.64%
Ideal Trend | 110 | 104.5 | 99 | 93.5 | 88 | 82.5 | 77 | 71.5 | 66 | 60.5 | 55 | 49.5 | 44 | 38.5 | 33 | 27.5 | 22 | 16.5 | 11 | 5.5 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days