## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 69
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Character Animations - Joseph | 20 | 5 | -15 | 5 | -10 | 0 | 4 | 4 | 0 | 3 | 0 | 4 | 4 | 5 | 3 | [6 empty] | 8 | 60%
Character Models - Joseph | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | 0 | [6 empty] | 25 | -150%
Shield Powerup Implementation - Austin | 6 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2 | 66.67%
Other Powerup - Austin | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | [5 empty] | 0 | 1 | 83.33%
Main Menus - Jerry | 12 | 2 | 1 | 0 | 0 | 2 | 3 | 0 | 1 | -6 | 1 | 0 | 1 | 0 | 1 | [6 empty] | 6 | 50%
In-game Menus - Braydon | 15 | 1 | 0 | 2 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | -6 | [6 empty] | 9 | 40%
Feature 7 | [21 empty] | 0
Feature 8 | [21 empty] | 0
Feature 9 | [21 empty] | 0
Feature 10 | [21 empty] | 0
Feature 11 | [21 empty] | 0
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 69 | 61 | 75 | 65 | 75 | 71 | 62 | 58 | 55 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 51 | 26.09%
Ideal Trend | 69 | 65.55 | 62.1 | 58.65 | 55.2 | 51.75 | 48.3 | 44.85 | 41.4 | 37.95 | 34.5 | 31.05 | 27.6 | 24.15 | 20.7 | 17.25 | 13.8 | 10.35 | 6.9 | 3.45 | -2.3981e-14
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days